- Project start date and end date

The expected start date for the project will be 5/12/2025 and will end on 6/7/2025. The RA will be expected to work 15 hrs. a week during the time of this project.

- Describe your role as a RA

The RA will work as a research assistant on a health informatics related project. They will be responsible for conducting several iterations of stepwise regression analysis, building prediction models and assist with data visualizations. The RA will also be responsible for editing the methodology section of the anticipated abstract.

| 1. | 5/12-5/17 | - Perform basic exploratory data analysis to understand the data's characteristics. - Conduct proper imputation for missing data - Complete descriptive statistics. - Identify appropriate prediction model (e.g. Multivariable logistic regression) |
| --- | --- | --- |
| 2. | 5/18-5/24 | - Perform stepwise regression analysis (identify and select the correct approach) - Interpret the results. - Evaluate the model |
| 3. | 5/25-5/31 | - Build prediction model identified in Step 1. - Perform several iterations of the variable - Evaluate the model results |
| 4. | 6/1-6/7 | - Assist with drafting the abstract following the structure of a typical research paper (introduction, methodology, results, discussion, conclusion). - Assist with editing the methodology section of the abstract. |